## Product Backlog
PRODUCT BACKLOG
ID | Feature | Priority | Sprint 1 | Sprint 2 | Sprint 3
1 | Represent visually what the game will look like through storyboard and sketches | M | To do
2 | Execute a usability test | M |  | To do
3 | Improve the product with the feedback of users coming from the usability test | M |  | To do
4 | Define clearly the interactions between the game elements | M | To do
5 | Make clear how the gameplay works using flowcharts | M | To do
6 | Encode the game rules in an instructions book | M |  | To do
7 | Make the game physical to be able to play it | M |  |  | To do
8 | Produce an instructive** video and make it available online | S |  |  | To do
9 | Describe a winning strategy based on the game rules * | C |  |  | To do
10 | Translate the instruction book in another language, so that both English and Dutch versions are available | C |  |  | To do
* A winning strategy could be used in the future to implement an automatized computer opponent (AI).
** Instructive means that the video has the purpose of teaching the viewers how to play the game. It is not meant as a commercial to advertize the game.
NOTES:
A) The ID numbers you see in the first column are unique identifiers for the features. When you write a sprint backlog, remember to use the correct ID for each user story. For example, when you will write the user story about the winning strategy, you will have to use ID 9. The first sprint backlog you will write, contains (at least) user stories with ID 1, 4, 5 (see also the sheet "Sprint 1 Backlog" of this Excel file).
B) The acceptance criteria of a user story (see sprint backlog) must be measurable and objective, in order to have a clear answer to the question "Is the user story done?". For example, an acceptance criteria like "the sketches are nice" is not okay, because "nice" is not measurable and different persons can have different opinions on it.
C) A user story must be in the shape of "As ... I want to ... so that ...".

## Sprint 1
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As project member I want a visual representation of the game through storyboard and sketches so I can get a clearer view of the game. | M | 8 | - Create game pylons design - Create game board design | Board design: - Start - Winner tile - Normal tiles - Special tiles Pylonds design: - 3D models (4x)
4 | As a project member I want to know clear definitions of the interactions between the game elements so i can implement them correctly. | M | 5 | - Create game rules document | - Playing rules - Context rules - Expansion rules - Wrapper - Page numbers - Author - Date - Group id - Class
5 | As a product owner I want to have flowcharts that clearly visualize the gameplay so I can get a clear view of progress made whilst playing the game. | M | 2 | - Create gameplay flowcharts | - Start - End (win and lose) - Normal tiles - All kinds of special tiles - Basic game flow

## Sprint 2
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
2 | As project owner I want to have a usability test executed so I can explore improvements not known previously. | M | 5 | - Create usability test plan - Create usability test schedule - Excecute usability test - Document usability test findings | Test plan: - Physical requirements - Required people (amount) - General time plan - Whats should be tested - How it should be tested Test schedule: - Date - Time - People Test findings: - Document with findings
3 | As project member I want the to improve the product with the feedback of the users coming from the usability test to improve the product and fix mistakes. | M | 2 | - Create improvements list | - Ordered items to improve
6 | As a user I want a book that contains the rules of the game so I can easily learn the game mechanics. | M | 8 | - Design rule book - Write rule book in English - Print rule book | Design: - Design of rule book (images / layout) Writing: - Specific rules in English - Wrapper Print: - Physical English rule book

## Sprint 3
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
7 | As a user I want a physical version of the game so I can actually play it. | M | 2 | - Create absolute game design document - Print physical copy of game | Game design document: - Wrapper - Author(s) - Date - Group id - Class - Project - Board design - Board dimensions - Characters design - Characters dimensions - Accessories design - General rules - Context rules - Expansion rules Physical copy: - Physical copy
8 | As a user I would like a instruction video or tutorial so I can learn the game more easily. | S | 3 | - Create online instruction video for the game | - Youtube / Vimeo link - Rules - Strategy
9 | As a user I would like a clearly defined way to win the game because I don't want to figure it out myself. | C | 5 | - Create online tutorial for the game | - Youtube / Vimeo link - Advanced strategy - Tips / tricks
10 | As a user I would like the instruction manual to be in Dutch as well so I can play it with people that don't know english. | C | 2 | - Translate rule book to Dutch - Print rule book in Dutch | - Translated text - Physical Dutch rule book